## Execution Report
QA Status Report DD/MM/YYYY
Release ID | S.No | Story ID/Description | Status | Test Case Count
23.7.15 | 1 | SCRUM-29 Validate Login Page | Done | 8
| 2 | SCRUM-152 Validate Home Page | Done | 17
| 3 | SCRUM-195 Validate Product page | Done | 5
|  |  | Total | 30
Test case Status | No: of Test Case
Pass | 26
Fail | 4
In Progress | 0
Blocked | 0
Not Executed | 0
Not Applicable | 0
Total | 30

## Bug Report
Bug Report | [10 empty] | 69
Release ID | Sprint # | User Story ID | Bug ID | Bug Summary | Severity | Priority | Status | Workaround | Bug Assigned to | Bug Reported by
23.7.15 | Sprint 0 | SCRUM-29 | SCRUM-312 | User is able to click the Login button but an error message "Invalid credential" is not displayed and remain on the login page. | High | High | In Development | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-321 | User is able to click the Login button but an error message "Invalid credential" is not displayed and remain on the login page. | High | High | In Development | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-325 | User is be able to click the Login button but an error message "Invalid credential" is not displayed and remain on the login page. | High | High | In Development | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-335 | User is unable to click the login button and a validation message "Please fill out this field" is not dispalyed after clicking the login button and remain on teh same page. | Medium | Medium | Done | No | Neha Liz | Niveditha Prasad
|  | SCRUM-152 | SCRUM-269 | User is able to click on the Admin icon but unable to view the profile . | High | High | In Development | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-344 | User is unable to click on the Sales menu and cannot view the Sales page . | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-345 | User is unable to click on the Stores menu and cannot view the Stores page. | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-346 | "HYATT" logo is not displayed | Low | Low | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-347 | User is unable to click on the Expense menu and cannot view the Expense page. | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-348 | User is unable to click on the Report menu and cannot view the Report page . | High | High | Done | No | Neha Liz | Niveditha Prasad
|  | SCRUM-195 | SCRUM-336 | Search results matching the entered keyword is not displayed. | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-337 | User is unable to click the confirmation pop up "Yes,Delete it!"and selected product is not deleted from the product list. | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-338 | User is unable to click the View button and selected product and details is not displayed in the "View Product " pop up table. | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-339 | User is unable to edit the Product Details in the Edit Form . | High | High | Done | No | Neha Liz | Niveditha Prasad
|  |  | SCRUM-340 | User is unable to click the print button in the stock preview dialog box | Medium | Medium | Done | No | Neha Liz | Niveditha Prasad
Severity | Bug Count |  |  |  |  | Bug Status | Bug Count
Showstopper | 0 |  |  |  |  | New | 0
Critical | 0 |  |  |  |  | Active | 4
Medium | 2 |  |  |  |  | Ready to Test | 0
High | 12 |  |  |  |  | Closed | 11
Low | 1 |  |  |  |  | Re-Open | 0
Total Bugs | 15 |  |  |  |  | Rejected | 0
[6 empty] | Total | 15